## Sheet1
AEITI - 2019 Work Plan
Objective 1: Increase public awareness of the sector’s current and potential contribution in order to enable a more informed, evidence-based public debate.
Rationale: Afghanistan is endowed with significant mineral resource potential. However, the sector's potential revenue contribution depends upon the commencement of mineral production in a number of high-profile large-scale mining projects. There is a misperception among stakeholders that this will happen in the short and medium term. AEITI will work to educate and inform the public on government's activities in this sector, stimulate public debate and public involvement in the sector, and also establish realistic public expectations of sector development.
Governance-related challenges: : 1. Current public expectations for extractive sector revenue are unrealistic. 2. There is little understanding of how the sector is managed. 3. There is a lack of awareness of the scale and potential value to the government of improving the formalisation of artisanal and small scale mining.
Outcome | Activity | Responsible | Deadline | Costs | Fund Source
Develop a Communication strategy, develop capacity of stakeholders staffs, publish EITI reports and annual progress reprot. | Develop communication strategy (three year plan). | AEITI SE | 2019-04-30 | NA | NA
| Establish and operationalise MSG Communications Working Group. | MSG | 2019-05-19 | NA | NA
| Train journalists and CSOs on extractive industries: how the Transparency system works and how to use it. | MoMP/ARD | 2019-03-30 | 1250 | GIZ
| CSOs to develop and organise campaigns in coordination with TWG. | CSO/TWG | 2019-05-30 | NA | NA
| CSOs to hold regional workshops to create public debate on the extractives sector in 4 regions of Afghanistan. | TWG/AEITI SE | 2019-12-30 | 12000 | WB
| 3 Workshops and capacity building of local stakeholders on EITI Global Standards and its requirements. | AEITI SE | 2019-03-30 | NA | NA
| Publish 6th EITI summary reports, briefings and infographics as a means of communicating with stakeholders. | AEITI SE | 2019-07-30 | NA | NA
| Disseminate hard and soft copies of the 6th EITI Report widely across Afghanistan. | AEITI SE | 2019-10-30 | 6000 | WB
| Redesign & Maintain an up to date website with links to data & social media subscriptions. | AEITI SE | 2019-12-31 | 2000 | WB
| Publish & disseminate 2018 AEITI Annual Progress Report. | MSG/SE | 2019-05-30 | NA | NA
Objective 2 Establish systematic disclosure and ensure the quality of EITI reporting from all relevant MOMP, and MoF departments
Rationale: EITI systematic disclosure forms the basis for transparency and facilitates public debate, disseminate information as well as provide a diagnostic means of assessing the health of the extractives sector in Afghanistan, and identify gaps and/or weaknesses in the government’s management of the sector across the value chain and provide recommendations for reform. EITI reports and communication activities can also be used to show-case the sector reform projects currently underway in Afghanistan which will improve the Government’s ability to manage the sector in a more transparent and equitable way.
Discrepancies in revenue data available to the MoMP and the MoF is a common problem due to non-standardised accounting practices at government, private sectior & SOEs.Systematic disclosure to the EITI standards will ensure accurate , timely and relevant information.
Outcome | Activity | Responsible | Deadline | Costs | Fund Source
Mainstream systematic disclosure within MOMP | Complete mapping of systematic disclosure to understand and identify sources of information for EITI reporting | AEITI SE | 2019-02-28 | NA | NA
| Public disclosure of mandatory social expenditures and Community Development Plan. Type of payment and beneficiary details | MSG/MoMP | 2019-02-28 | NA | NA
| Redesign the visualisation of currently available transparency data i.e. user-friendly experience required | IT/MSG | 2019-05-28 | NA | NA
| MOMP/MOF/SOE to produce and maintain auditable and accurate transparency related information and improve filing system | MSG/MoMP/MoF/SOE | 2019-08-28 | NA | NA
| Systematic disclosure of transparent tendering and bidding procedure; allocation process of licencing and licence transfers; disaggregated production values and volumes; export data; Non-Tax Revenues. | MSG/MoMP | 2019-12-30 | NA | NA
| Disclosure of Beneficial Ownership in accordance with the deadline of the EITI standard | MSG/MoMP | 2019-12-30 | NA | NA
| Publish comprehensive online extractive resource sector contract database that includes key terms of all winning contracts, social and environmental impact assessments and mitigation plans, and links to the relevant license in Dari, Pashto and English. | MSG/MoMP | 2019-09-30 | NA | NA
| Implement the systematic disclosure of SOE financial information: prevailing rules and practices; changes to ownership; loans and loan guarantees; and publication of existing studies and off-budget finances/quai-fiscal expenditures. | MSG/MoMP | 2019-06-30 | NA | NA
| Comprehensive data on extractive resource sector contribution to the economy and GDP to be made available. | MOF | 2019-06-30 | NA | NA
| Non tax revenues are comprehensively disclosed in easy-to-understand format, apart from the EITI Reconciliation Report | MoMP | 2019-03-30 | NA | NA
| Ensure the quality control and assurance during the data consolidation reporting process. | MSG/MoMP/MoF/SAO | 2019-03-30 | NA | NA
| Conduct training needs analysis of relevant staff of MOMP and MOF and assessments of MOMP, MOCI, MOF and ACD reporting systems. | MSG/MoMP/MoF/SOE | 2019-06-30 | NA | NA
Objective 3. Improve Relevant legal framework that governs extractive sector is checked for compliance with global EITI standards
Rationale: The draft mining law and regulations, which is currently in development needs to be updated to include transparency,EITI requirements, institutionalise extractives governance aimed at developing the Islamic Republic of Afghanistan as an investment destination for international and domestic extractives.
Outcome | Activity | Responsible | Deadline | Costs | Fund Source
Ensure that the drafting of the Comprehensive Mineral laws are compliant with EITI Standards | Hold consultations between the Legal Department of the MoMP and MSG, and selected civil society organizations to develop recommendations to address identified problems through amendments of the draft law or regulations | MSG/MoMP | 2019-04-30 | NA | NA
| Ensure that EITI Standards applicable to AEITI are considered and reflected in the Mineral's Legal Framework | NVM/Sr Advisor AEITI | 2019-05-28 | NA | NA
| Database (dedicated page on MoMP website) of relevant laws and regulations applicable to the extractive industries accessible online | MSG/MoMP | 2019-06-30 | NA | NA
Objective 4: Improve MSG participation and governance (ownership of EITI process) in order to achieve an effective AEITI
Rationale: . A well-functioning MSG is essential in order to put ideas into practice. This is something that has been found inadequate by the Validation and the Secretariat Review in the past, while there have also been concerns that the government was not sufficiently engaged.The effectiveness of the AEITI is dependant on the ability and capacity of the Multi Stakeholder Group- MSG. In order for AEITI to implement EITI requirements, the MSG needs to build its capacity to understand the EITI requirements, its application and acts as effective representatives of Afghan stakeholders
Outcome | Activity | Responsible | Deadline | Costs | Fund Source
AEITI Secretariat at the Ministry of Mines and Multi-Stakeholder Group (MSG) fully operational (with all relevant EITI corrective actions addressed) producing timely reports of high standards | Alignment of SE; transfer of AEITI Budget from MOF to MOMP; Preparation, approval and adoption of TOR for MSG & SE | MSG/MoMP | 2019-06-30 | NA | NA
| Review status of BO roadmap - comment and decide next steps. | MSG | 2019-05-30 | NA | NA
| Development of procedures/guidance for the MSG | NVM | 2019-05-30 | NA | NA
| Capacity building 'Study Tour' for MSG | MSG/SE | 2019-12-30 | 46000 | WB
| Capacity building training for AEITI Secretariat | AEITI SE/NVM | 2019-12-30 | 25200 | WB
| Operationalise MSG Working Groups | MSG | 2019-04-28 | NA | NA
| Address corrective actions from the Validation Report | MSG/MoMP/MoF/SOE | 2019-06-30 | NA | NA
| Participate in EITI International conferences and workshops | MSG/SE | 2019-12-30 | 19500 | WB
Objective 5: Production & Publication of AEITI Reports
Rationale: EITI reports is the key means of disseminating information to stakeholders and the International community. Afghanistan's progress is also judged by the information contained therein. As such, the EITI report is currently the key means of information until systematic disclosure systems become fully operational.
Outcome | Activity | Responsible | Deadline | Costs | Fund Source
Afghanistan EITI reports (including summaries) prepared and submitted to the EITI Secretariat and published. | ToRs for IA for 7th EITI Report finalised | MSG | 2019-08-30 | NA | NA
| Hiring of consultancy firm for resolving discrepancies found in the 4th & 5th AEITI Report | MSG/SE | 2019-06-19 | 20000 | WB
| Hiring of Consultancy for Developing the 6th EITI Report | MSG | 2019-01-30 | 111000 | WB
| Presentation and Approval of the 6th EITI report (MSG Meeting) | MSG/IA | 2019-06-10 | NA | NA
| Publishing of the 6th EITI Report (Launch) | MSG/SE | 2019-06-20 | NA | NA
| Workshop -lessons learned from 6th EITI Report and disseminate findings/learning to the relevant stakeholders | MSG/SE | 2019-08-19 | 2000 | GIZ
| Hiring of Consultancy for Developing the 7th EITI Report | MSG/SE | 2019-11-30 | 120000 | WB
| Presentation and Approval of the7 th EITI report (MSG Meeting) | MSG/IA | 2020-04-20 | NA | NA
| Publishing of the 7th EITI Report (Launch) | AEITI SE | 2020-04-30 | NA | NA
| Workshop -lessons learned from 7th EITI Report and disseminate findings/learning and prepare case studies where possible. | MSG/SE | 2020-06-30 | 2000 | GIZ
Objective 6: Successful Validation of AEITI
Rationale: In order for AEITI to be recognised as an EITI country, Validation is a necessary step. In order to achieve validation, comments from the last validation reports MUST be addressed as a precursor to a successful EITI Validation of Afghanistan.
Outcome | Activity | Responsible | Deadline | Costs | Fund Source
Adress all comments and achieve a successful EITI Validation. | Address validation comments to ensure "Meaningful Progress" | MSG | 2019-08-30 | NA | NA
| Conduct internal self-assessment to evaluate the impact on addressing (2018 Validation) recommendations | MSG/SE | 2019-06-30 | 20400 | GIZ
| Request official Re-Validation from EITI Board along with Global Conference in Paris | MSG/SE | 2019-06-30 | NA | NA